## TestPlan
Test Plan For exchange-tradex.nftarttoken.xyz
1 | Test Plan ID: | tradex_TC001
2 | Introduction: | TradeX is an exchange where you can trade directly on world events like inflation rate, movies collections or the next president. We are removing chaos from stock trading tools and providing direct exposure to events which affects asset prices and super simple to understand
3 | Test Items: | User Management: Signup - Login - Logout - Forgot Password - Reset Password - 2FA Security Method Unavailable? - Security Settings
4 | References: | Requirements, Project Plan ,Test Strategy — Use cases (If available) High Level Design doc , Low Level design docs, Process guide line doc, Prototypes.
5 | Features to be Tested: | User Management: Signup - Login - Logout - Forgot Password - Reset Password - 2FA Security Method Unavailable? - Security Settings
6 | Features not to be Tested: | N/A
7 | Entry Cirteria: | A. Test Design Team formation, Responsibilities, Schedule, Requirements. Test Case Template etc. Training on Domain on Manual testing tools. B. Test Execution: Readiness of Test Lab, Readiness of AUT Requirements Test Case docs, Test Data, Defect Report Template etc...
8 | Exit Criteria: | All possible test cases executed, Maximum defects fixed, Final Regression performed successfully, Confidence on Test process, Time Limitations, Budget Limitations
9 | Suspension Criteria:
10 | Roles & Responsibilities: | Fazle Rabbi Software Tester Test planning, Test Case writing, Report writing, Bug Reporting etc
11 | Schedule: | Task Days Duration Remarks 1. Understanding & Analyzing Requirements 18th April 2023 2. 19th April review meeting 3. 20th April generating test scenarios 4. 21st April review test plan 5. Test case documentation 21st April 6. Reviews 22nd April
12 | Traning: | Training Program on SQA Manual testing training using mindMap tool
13 | Risk & Mitigation: | Team member's issues Time Budget
14 | Test Deliverable: | Test plan, Review Reports, Test Case, Test data opened, Closed defect reports, Test Summary Report & Mindmap
15 | Approval: | 1. Test plan documentation; Muhi (Tester) 2. Review Name (QA Analist) 3. Approval Name (Project Manager)

## TestCase
Product Name |  | Tradex | TC Start Date | 19/04/2023 | TC Execution Start Date | 19/04/2022 |  | TEST CASE
Module Name |  | Test case for Reship Global Shipping | TC End Date | 24/04/2023 | TC Execution End Date | 22/04/2023 |  | PASS | 100
Epic |  |  | Test Case Developed By | Rabbi | Browser (tested) | Yes |  | FAIL | 1
Developer Name (TL) |  |  | Test Case Reviewed By | Rabbi | Performance (tested) | Yes |  | Not Executed | 0
[8 empty] | Out of Scope | 0
[8 empty] | TOTAL | 101
#TestCase ID | Module | Feature | Test Case | Expected Result | Actual Result | Test Data | Reproducing Steps | Bug Screenshots | Status | Remarks
TC001 | User Management | Sign Up | URL opens Tradex home page or not? | Should open tradex home page | found as per expectations. | https://exchange-tradex.nftarttoken.xyz/ |  |  | Passed
TC002 |  |  | Signup button takes to signup page on not | A sign up UI should apear | found as per expectations. |  |  |  | Passed
TC003 |  |  | Grammatical or spelling mistake on sign up page | No grammatical or spelling mistake | found as per expectations. |  |  |  | Passed
TC004 |  |  | SignUp with google takes to 'sign in with google' page | Should open up gmail pick page | found as per expectations. |  |  |  | Passed
TC005 |  |  | SignUp with Apple Id | Should open up apple id and connection bridge page | found as per expectations. |  |  |  | Passed
TC006 |  |  | Clicking 'sign up' button leaving all fields empty | should light up all the empty boxes with red color border, give message to fill up the fields. Shouldn't take to next page | found as per expectations. | no data given |  |  | Passed
TC007 |  |  | Giving numbers as input email address | Should give "invalid mail" message. | found as per expectations. | 123456 |  |  | Passed
TC008 |  |  | Giving random alphabet as email address | Should give "invalid mail" message. | found as per expectations. | asdfgaasdf |  |  | Passed
TC009 |  |  | Alphabet, numbers and special character as email address | Should give "invalid mail" message. | found as per expectations. | askdjfhl232345&^%&^ |  |  | Passed
TC010 |  |  | input random mail address | should give "Invalid e-mail address" message | Accepts the mail address | $$@gzz.com 12@gg.com bb@12.com kik_k@yy.com | 1. Go to url "https://exchange-tradex.nftarttoken.xyz/" 2. Click on "Sign Up" button. 3. Click 'e-mail' field 4. input "$$@gzz.com" 5. Click "Sign Up" button | Click me | Failed
TC011 |  |  | input random mail address | should give "Invalid e-mail address" message | found as per expectations. | ?kik@gmail.com \ki_k@gmail.com |  |  | Passed
TC012 |  |  | Input "already used mail id" | should give "Email Already Used" message | found as per expectations. |  |  |  | Passed
TC013 |  |  | If password not provided | Should prompt to password is required | found as per expectations. |  |  |  | Passed
TC014 |  |  | Inputting any character as password | Should Password must be at least 8 characters and contain at least one uppercase, one lowercase, one number and one special character | found as per expectations. | sadlkDD2345*(&^ |  |  | Passed
TC015 |  |  | 3 or less characters as password | Should Password must be at least 8 characters and contain at least one uppercase, one lowercase, one number and one special character | found as per expectations. | 123 |  |  | Passed
TC016 |  |  | Refferral id(optional) | should not mandatory | found as per expectations. |  |  |  | Passed
TC017 |  |  | Leaving agreement button | Should give You must accept the agreement to sign up | found as per expectations. |  |  |  | Passed
TC018 |  |  | clicking sign up button after giving all the right inputs | should accept | found as per expectations. |  |  |  | Passed
TC019 |  | Log In | Verifying whether Sign In page appears | A Sign In UI should apear | found as per expectations. |  |  |  | Passed
TC020 |  |  | Grammatical or spelling mistake on Sign In page | No grammatical or spelling mistake | found as per expectations. |  |  |  | Passed
TC021 |  |  | Clicking "Google" API for Sign In | Should connect to a google sign in page if google ID is signed out before. | found as per expectations. |  |  |  | Passed
TC022 |  |  | Clicking "Apple" API for sign in | should connect to a apple sign in page if apple ID is sighed out before | found as per expectations. |  |  |  | Passed
TC023 |  |  | Clicking sign in button with empty fields | Should appear an error message | found as per expectations. |  |  |  | Passed
TC024 |  |  | Clicking sign in button with empty password field | Should appear an error message | found as per expectations. | Email: Rabbi@gmail.com pass: |  |  | Passed
TC025 |  |  | Clicking sign in button with empty email field | Should appear an error message | found as per expectations. | email: pass: 12345678 |  |  | Passed
TC026 |  |  | Valid e-mail and invalid password | Should appear an error message | found as per expectations. | Email: rabbi@gmail.com pass: 87654321 |  |  | Passed
TC027 |  |  | Valid password and invalid e-mail | Should appear an error message | found as per expectations. | email: r@gmail.com pass: 12345678 |  |  | Passed
TC028 |  |  | invalid password and e-mail | Should appear an error message | found as per expectations. | email: r@gmail.com pass: 87654321 |  |  | Passed
TC029 |  |  | valid e-mail and password | Should appear the home page | found as per expectations. | email: rabbi@gmail.com pass: 12345678 |  |  | Passed
TC030 |  |  | Checking password field is masked | Written password should be masked | found as per expectations. | Pass: 12345678 |  |  | Passed
TC031 |  |  | Clicking pick icon on password field | Written password should be visible | found as per expectations. | Pass: 12345678 |  |  | Passed
TC032 |  |  | Checking "Forgot password" hyperlink | should lead to a recovery code page | found as per expectations. | N/A |  |  | Passed
TC033 |  |  | Remember me checkbox checkable or not | Checkbox should be checked or unchecked depending on the previous state | found as per expectations. | N/A |  |  | Passed
TC034 |  |  | Remember me functionality works when checked | Home page should appear | found as per expectations. | N/A |  |  | Passed
TC035 |  |  | Remember me functionality works when unchecked | Sign in UI should appear | found as per expectations. | N/A |  |  | Passed
TC036 |  |  | Clicking "Sign Up Now" hyperlink | Sign up UI should appear | found as per expectations. | N/A |  |  | Passed
TC037 |  |  | Labeling of all field | All field should be left allign | found as per expectations. | N/A |  |  | Passed
TC038 |  |  | If "Remember me" checkbox is by default checked | Checkbox should not be by default checked | The checkbox is by default checked | N/A | 1. Go to "https://exchange-tradex.nftarttoken.xyz/" 2. Click on "Sign In" button. 3. Sign In page will appear. 4. Check if "Remember me" is by default checked |  | Passed
TC039 |  |  | Verify if the app allows multiple sign in from different devices at the same time | Should allow multiple sign in from multiple devices | found as per expectations. |  |  |  | Passed
TC040 |  | Log out | The log out option should not be visible till the user is logged in | Log out option invisible before log in | found as per expectations. |  |  |  | Passed
TC041 |  |  | Verify that pressing log out button takes user to log in page | Log in page should appera | found as per expectations. |  |  |  | Passed
TC042 |  |  | Verify that browser back button takes user to log in page | Should take user to the log in page | found as per expectations. |  |  |  | Passed
TC043 |  |  | verify that browser back button should not take user to the previous page | should not take user to previous page | found as per expectations. |  |  |  | Passed
TC044 |  |  | verify the spelling of the log out option | No gramattertical spelling mistake | found as per expectations. |  |  |  | Passed
TC045 |  |  | verify fonts visibility | Should be clearly visible | found as per expectations. |  |  |  | Passed
TC046 |  |  | verify if the log out link or button clickable when logged in | Should be able to click the button or link | found as per expectations. |  |  |  | Passed
TC047 |  |  | Verify by Clicking on the sign-out button without an internet connection and reconnecting to the internet to check if it’s properly logout or not. | Should be able to logout successfully | found as per expectations. |  |  |  | Passed
TC048 |  |  | Does the website remember the username after log out? | Should remember username | found as per expectations. |  |  |  | Passed
TC049 |  |  | Verify the log out button easy to find | Should be easily locatable | found as per expectations. |  |  |  | Passed
TC050 |  |  | Does the power outage retain the session if not signed off? | Should not retain the session | found as per expectations. |  |  |  | Passed
TC051 |  |  | Is the sign-off button or link broken after clicking? | Should not be a broken link | found as per expectations. |  |  |  | Passed
TC052 |  | Forgot Password | Check if the forgot password option is shown below after the wrong password is entered. | Should shown in below | found as per expectations. |  |  |  | Passed
TC053 |  |  | Verify if the forgot password link is working correctly and landing on the correct page. | Should forgot password link is working correctly | found as per expectations. |  |  |  | Passed
TC054 |  |  | Check if the forgot password link is directed to the right page i.e. forgot password page. | Should showed perfectly | found as per expectations. |  |  |  | Passed
TC055 |  |  | Verify that the link to change the password is sent to the user’s emailId only. | should sent to the user’s emailId only | found as per expectations. |  |  |  | Passed
TC056 |  |  | Verify that the security questions asked are the same as the ones that the user entered during sign-up. | should asked | found as per expectations. |  |  |  | Passed
TC057 |  |  | Verify that if a wrong answer is entered to any security question, it should not proceed to the next question. | Should be showed wrong | found as per expectations. |  |  |  | Passed
TC058 |  |  | Verify that the new password matches with required specifications for the password value. For example, it should allow a combination of special characters, upper case characters, numerics, etc. | Should allow a combination of special characters, upper case characters, numerics, etc. | found as per expectations. |  |  |  | Passed
TC059 |  |  | Verify that the login should be possible with the newly changed password. | Should be able to login successfully with new password | found as per expectations. |  |  |  | Passed
TC060 |  |  | Check if the link gets expired once the user has set a new password. | Should be set new password and break page | found as per expectations. |  |  |  | Passed
TC061 |  |  | Check if the link is live/applicable for one-time use only. | Should be use link for one time | found as per expectations. |  |  |  | Passed
TC062 |  |  | Verify that the link is working only for a specified period of time and then shows a time-out message. | Should work it perfect | found as per expectations. |  |  |  | Passed
TC063 |  |  | Verify that the user should not be allowed to request forgot password frequently. | Should nor be ask frequently | found as per expectations. |  |  |  | Passed
TC064 |  | Reset Password | Check if the “can’t access your account” works. | should redirect the user to the correct page. | found as per expectations. |  |  |  | Passed
TC065 |  |  | Check if the “can’t access your account” link redirects to the correct page. | should have the necessary option for a password reset. |  |  |  |  | Passed
TC066 |  |  | Check if the redirected page has the necessary option for a password reset. | should ask the user to choose between three options for a password reset. | found as per expectations. |  |  |  | Passed
TC067 |  |  | Check if the page asks to choose between three options for a password reset. | should take the user to the necessary page for a password reset. | found as per expectations. |  |  |  | Passed
TC068 |  |  | Check if the link “I forgot my password” option takes you to the necessary page for a password reset. | should offer specific instructions to that page. | found as per expectations. |  |  |  | Passed
TC069 |  |  | Check if the link “I know my password, but I can’t sign in” page offers specific instructions to that page. | should redirect the user to the specific page. | found as per expectations. |  |  |  | Passed
TC070 |  |  | Check if the link “I think someone else is using my Microsoft Account” is to the specific page. | should not take user to previous page | found as per expectations. |  |  |  | Passed
TC071 |  |  | Check if the next and cancel buttons are disabled if no choice in the radio button is made. | should be disabled if no choice in the radio button is made. | found as per expectations. |  |  |  | Passed
TC072 |  |  | Check if the option selection enables the next and cancel buttons. | should enable the next and cancel buttons. | found as per expectations. |  |  |  | Passed
TC073 |  |  | Check if the correct email ID and captcha redirect the user to the next page for password extraction. | should proceed as expected. | found as per expectations. |  |  |  | Passed
TC078 |  |  | Check if the mobile number verification process is triggered after selection. | hould proceed as expected. | found as per expectations. |  |  |  | Passed
TC079 |  |  | Check if the secret question verifies the right answer. | Should remember username | found as per expectations. |  |  |  | Passed
TC080 |  |  | Check if following the specific instruction (as per the account’s country of origin) leads to a password reset. | should lead to a password reset. | found as per expectations. |  |  |  | Passed
TC081 |  |  | Check if the password reset process allows the user to set a new password. | should allow the user to set a new password. | found as per expectations. |  |  |  | Passed
TC082 |  |  | Check if the process allows the user to set a new password with the same restriction on the registration page. | should allow the user to set a new password with the same restriction on the registration page. | found as per expectations. |  |  |  | Passed
TC083 |  | 2FA Security Method | Access the web application or service and enter your username and password. | should complete successfully, and the user should be logged in. | found as per expectations. |  |  |  | Passed
TC084 |  |  | Once the credentials have been entered, the system should prompt for the second factor authentication. | should complete successfully, and the user should be logged in. | found as per expectations
TC085 |  |  | Enter the code generated by the authenticator app or device and click on verify. | should complete successfully, and the user should be logged in. | found as per expectations. |  |  |  | Passed
TC086 |  |  | Verify that the code is valid and the user is logged in. | should complete successfully, and the user should be logged in. | found as per expectations |  |  |  | Passed
TC087 |  |  | Repeat step 3 using an invalid code. | should fail, and the system should prompt the user to enter a valid code. | found as per expectations. |  |  |  | Passed
TC088 |  |  | Verify that the system rejects the invalid code and prompts the user to enter a valid code. | should complete successfully, and the user should be prompted to enter a valid code. | found as per expectations |  |  |  | Passed
TC089 |  |  | Try to log in using the correct username and password without entering the second factor authentication code. | should fail, and the system should prompt the user to enter the second factor authentication code. | found as per expectations. |  |  |  | Passed
TC090 |  |  | Verify that the system requires the second factor authentication code to complete the login process. | should complete successfully, and the system should prompt the user to enter the second factor authentication code. | found as per expectations |  |  |  | Passed
TC091 |  |  | Try to log in using an incorrect username and password. | should fail, and the system should prompt the user to enter the correct username and password. | found as per expectations. |  |  |  | Passed
TC092 |  |  | Verify that the system prompts the user to enter the correct username and password before requiring the second factor authentication code. | should complete successfully, and the system should prompt the user to enter the correct username and password before requiring the second factor authentication code. | found as per expectations |  |  |  | Passed
TC093 |  | Security Settings | attempt to create a new user account with a weak password, and verify that the web application requires a strong password with a minimum number of characters, symbols, and uppercase and lowercase letters. | Should the web application should prompt the user to create a strong password that meets the specified requirements. | found as per expectations. |  |  |  | Passed
TC094 |  |  | attempt to log in to the web application and then log out. Then, attempt to use the back button on the browser to see if the user is still logged in. The user should be required to log in again. | Should web application should require the user to log in again when attempting to access protected resources after logging out or closing the browser. | found as per expectations. |  |  |  | Passed
TC095 |  |  | attempt to access restricted areas of the web application without logging in. Verify that the web application requires authentication before granting access to protected resources. | Should web application should not allow access to protected resources without proper authentication. | found as per expectations. |  |  |  | Passed
TC096 |  |  | attempt to enter invalid input into fields on the web application. Verify that error messages are displayed that do not reveal sensitive information, such as database or system error messages. | web application should display appropriate error messages when invalid input is entered. | found as per expectations. |  |  |  | Passed
TC097 |  |  | attempt to enter malicious code, such as SQL injection, into fields on the web application. Verify that the web application properly validates input to prevent attacks. | Should web application should properly validate input and prevent the injection of malicious code, such as SQL injection attacks. | found as per expectations. |  |  |  | Passed
TC098 |  |  | verify that sensitive information, such as passwords and user data, are encrypted in transit and at rest using industry-standard encryption algorithms. | Sensitive information, such as passwords and user data, should be encrypted in transit using HTTPS and at rest using industry-standard encryption algorithms. | found as per expectations. |  |  |  | Passed
TC099 |  |  | attempt to access the web application using different user roles, such as an admin user and a regular user. Verify that each user is granted the appropriate level of access to resources. | Shouldweb application should grant each user the appropriate level of access to resources based on their user role. | found as per expectations. |  |  |  | Passed
TC100 |  |  | attempt to inject malicious code into the web application through input fields, such as a search box. Verify that the web application properly sanitizes input to prevent XSS attacks. | Should web application should properly sanitize input to prevent XSS attacks. | found as per expectations. |  |  |  | Passed
TC101 |  |  | verify that third-party integrations, such as social media logins or payment gateways, are properly secured and comply with industry standards and regulations. | Should standards and regulations. | found as per expectations. |  |  |  | Passed

## Report
Test Case Report
Project Name - | Spotify.com
Module Name - | User Management |  |  |  |  | Total No. | Status | Result :
Test Case Version | - |  |  |  |  | 100 | PASS
Written By | AL MUTASIM HASAN MUHI |  |  |  |  | 1 | FAIL
Executed By | AL MUTASIM HASAN MUHI |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment :
Reviewed By | - |  |  |  |  | 0 | Out of Scope |  |  | Test Environment | Google Chrome Browser
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 100 | 1 | 0 | 0 | 101
Grand Total | 100 | 1 | 0 | 0 | 101
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## BugReport
Bug Reporting
TC010
Issue: Accpeting email address that does not showed any warning message
Reproducing Steps:
1. Go to url "https://exchange-tradex.nftarttoken.xyz/"
2. Click on "Sign Up" button.
3. Click 'e-mail' field
4. input "%$^56@gmail.com"
5. Click "Sign Up" button
Env: Production
Module: Sign Up
Severity: P2
Screenshot: Click me
Responsible QA: Fazle Rabbi

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result
1 | Percentage of Test Cases Executed | (No. of Test cases executed / Total no. of Test cases written) * 100 | 101
2 | Percentage of Test Cases not Executed | (No. of Test cases not executed / Total no. of Test cases written) * 100 | 0
3 | Percentage of Test Cases Passed | (No. of Test cased passed / Total no. of Test Cases Executed) * 100 | 100
4 | Percentage of Test Cases Failed | (No. of Test cases failed / Total no. of Test Cases Executed) * 100 | 1
5 | Percentage of Test Cases Blocked | (No. of Test cases blocked / Total no. of Test Cases Executed) * 100 | 0
6 | Defect Density | No. of Defects found / Size (No. of requirement) | N/A
7 | Defect Removal Efficiency | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of defects found in UAT / No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of defects rejected / Total no. of defeccts raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported Date | N/A
11 | Customer Satisfaction | No. of complaints per period of time